## TASKS
TASK LIST
MY TASKS | OWNER | START DATE | DUE DATE | % COMPLETE | DONE | NOTES
Sign MOU | Team + Librarian | Date | Date | 0% | 0
Forumlate Review Question | Team | Date | Date | 0% | 0
Locate Previous Reviews | Librarian | Date | Date | 0% | 0
Write Protocol | Team | Date | Date | 0% | 0
Review Protocol | Librarian | Date | Date | 0% | 0
Finalize Protocol | Team | Date | Date | 0% | 0
Draft Search | Librarian | Date | Date | 0% | 0
Review Search | Team | Date | Date | 0% | 0
Finalize Search | Librarian | Date | Date | 0% | 0
Translate Search | Librarian | Date | Date | 0% | 0
Run Search | Librarian | Date | Date | 0% | 0
Deduplicate Search | Librarian | Date | Date | 0% | 0
Register Protocol | Team | Date | Date | 0% | 0
Upload Pilot Screen | Librarian | Date | Date | 0% | 0
Pilot Screen | Team | Date | Date | 0% | 0
Upload T/A Screen | Librarian | Date | Date | 0% | 0
Title Abstract Screen | Team | Date | Date | 0% | 0
Locate Full Text | Librarian | Date | Date | 0% | 0
Full Text Screen | Team | Date | Date | 0% | 0
Snowball References (if desired) | Team + Librarian | Date | Date | 0% | 0
Data Extraction | Team | Date | Date | 0% | 0
Data Synthesis | Team | Date | Date | 0% | 0
Search Update (if applicable) | Librarian | Date | Date | 0% | 0
Meta Analyze (if applicable) | Team | Date | Date | 0% | 0
Manuscript Write Up | Team | Date | Date | 0% | 0
Search Methods for Manuscript | Librarian | Date | Date | 0% | 0
Manuscript Review | Team + Librarian | Date | Date | 0% | 0